## Slide 1
Social Interactivity Mentor for Youth with Autism using the NAO Robot (SIMYAN)
Andrew Nguyen | Bryce George | Colton Homuth | William Ross
Sponsor - Dr. Adham Atyabi
Faculty Advisor - Mr. Bill Michael
March 5, 2021
Social Robotics 2
Weekly Report for 1-5 March 2021

## Slide 2: Project Status
Current Phase: Development
  Started: 2/1
  Ends: 4/11
Current Sprint: 2 (of 6)
  Started: 2/22
  Ends: 3/7
  Days Remaining: 3
Epics:
  Core SDK [AT RISK]
    Activities Master Module [In Progress – 80%]
    Adv. Speech Recognition Module [In Progress – <50%]
    Adv. Motor Control Module [Not Started]
    Adv. Computer Vision Module [In Progress – <50%]
Overall Status: At Risk

## Slide 3: Development Accomplishments
Run activities and services from remote machine
  tested successfully
Activities Master Module prototype
  registers services on start up
  unregisters them on stopping
QiChat syntax tested
Jetson Nano OS setup
qi Framework installed on Jetson Nano
  testing 3/5 (see Impediments)
OpenCV algorithms tested

## Slide 4: Parts Acquisition
Xbox Kinect ordered and arrived.
Wi-Fi Antenna ordered, arriving 3/5.
Rubber Washers purchased.

## Slide 5: Impediments
OS incompatibility
  NAOqi Framework only officially supported for Ubuntu 16.04
  Jetson Nano only supports Ubuntu 18.04
  Solution:
  Found compiled qi Framework binaries and Python bindings for Ubuntu 18.04
    Found and installed 3/4
    Testing 3/5
Unfamiliarity w/ NAOqi SDK & add’l utilities
  Specialized framework
  Broad scope w/ marginal supporting documentation
  Solution:
  Identified core points of understanding and collected links/resources covering them.
    Team required to read and review by 3/5
    Will be included in support documentation for project

## Slide 6: Implementation Modifications
Run SIMYAN from Jetson Nano
  Possible, assuming testing w/ qi Framework is successful (3/5)
  Run remote qi Application on Jetson Nano, which handles all SIMYAN processing
  Connection options:
    Connect Jetson Nano and NAO to the same Wi-Fi network
    Setup Jetson Nano as Wireless Access Point and connect NAO to it

## Slide 7: Schedule Updates
Extending Core SDK development into Sprint 3
If Jetson Nano can run SIMYAN:
  No need to create separate program to provide Jetson Nano services
  Everything handled via qi Framework
  Much simpler and faster to implement
Drawing Activity Module development pushed back to 3/15

## Slide 8: Any Questions?