## Slide 1
Social Interactivity Mentor for Youth with Autism using the NAO Robot (SIMYAN)
Andrew Nguyen | Bryce George | Colton Homuth | William Ross
Sponsor - Dr. Adham Atyabi
Faculty Advisor - Mr. Bill Michael
March 12, 2021
Social Robotics 2
Weekly Report for 8-12 March 2021

## Slide 2: Project Status
Current Phase: Development
  Started: 2/1
  Ends: 4/11
Current Sprint: 3 (of 6)
  Started: 3/8
  Ends: 3/23
  Days Remaining: 11
Epics:
  Core SDK [AT RISK]
    Activities Master Module [In Progress – 90%]
    Adv. Speech Recognition Module [In Progress – ~50%]
    Adv. Motor Control Module [In Progress - <10%]
    Adv. Computer Vision Module [In Progress – ~50%]
Overall Status: At Risk

## Slide 3: Development Accomplishments
qi Framework tested on Jetson Nano
  Test run w/ Activities Master Module successful
Added WiFi adapters to Nano
  Edimax EW-7611ULB
  EDUP Wireless Network Adapter
Setup wireless access point for Nano
  Started automatically when at least one adapter present
  Shares IP with connected devices when Nano connected to internet on another network

## Slide 4: Parts Acquisition
Xbox Kinect
Xbox Kinect Cable Adapter
Wi-Fi Adapters (x2)
Rubber Washers

## Slide 5: Impediments
Schedule/Workload
  Conflicts from work/class/extracurricular schedules
  Midterms/Projects
Motor Control System Complexity
  Specification format
  Scaling, feature prioritization, and boundary extraction
  Realtime drawing surface bounds checking
  Coordinate transformation series from image space to end-effector space
  Motion calibration

## Slide 6: Implementation Modifications
Run SIMYAN from Jetson Nano (Update)
  Necessary facilities tested and working
  Jetson Nano hosts wireless Access Point which NAO can connect to
  Verified implementation strategy

## Slide 7: Schedule Updates
Extending Core SDK development through end of Sprint 3
Primary development effort towards Motor Control System for remainder of sprint
Drawing Activity Module development pushed back to 3/24

## Slide 8: Any Questions?