## Slide 1
Social Interactivity Mentor for Youth with Autism using the NAO Robot (SIMYAN)
Andrew Nguyen | Bryce George | Colton Homuth | William Ross
Sponsor - Dr. Adham Atyabi
Faculty Advisor - Mr. Bill Michael
April 9, 2021
Social Robotics 2
Weekly Report for 5-9 April 2021

## Slide 2: Project Status
Current Phase: Development
  Started: 2/1
  Ends: 4/18
Current Sprint: 4 (of 6)
  Started: 3/24
  Ends: 4/11
  Days Remaining: 3
Epics:
  Core SDK [CRITICAL]
    Activities Master Module [In Progress – 90% (Paused)]
    Adv. Speech Recognition Module [In Progress – 75%]
    Adv. Motor Control Module [In Progress – 70% ]
    Adv. Computer Vision Module [In Progress – 70%]
  Drawing Activity [CRITICAL]
    Drawing Specification Generator [In Progress < 50%]
    Activity User Interaction Flow [Not Started]
    Motor Control Integration [Blocked]
    Vision Integration [Blocked]
    Speech Integration [Blocked]
    Kinect Integration [Not Started]

## Slide 3: Development Accomplishments
SIMMotorControl service interface defined and stubbed out in code
(probably more)

## Slide 4: Impediments
Schedule/Workload
  Easter weekend
  Conflicts from work, class, and extracurricular schedules

## Slide 5: Schedule Changes & Triage Plan
Extending Development phase by 1 week
  New end date 4/18
  Afterward:
    1 week for testing & final dev
    1 week for documentation
    1 week for final presentation prep.
Triage Plan:
  Goals
    Finish all Core SDK Epics by 4/11
    Complete all Drawing Activity Epics by 4/18
  If unsuccessful reaching goals:
    Rescope development based on what can be finished within <= 12 (total) add’l hours of work
    All dev & testing halts completely 4/27

## Slide 6: Any Questions?